## Sheet1
Task Description | Estimated Time (Hours) | Actual Time (Hours) | Start Date | End Date | Priority | Assigned To | Comments/Notes
CV React - Edit Deductions on Settlements | 12 | 20 | 2023-09-20 | 2023-09-23 | High | Awais Subhani
No manifests created yet button green with Arrive text. | 8 | 7 | 2023-10-27 | 2023-11-28 | High | Awais Subhani
When a Manifest has been created and receipt generated (all receipts generated in case of multiple manifests) change the button color to yellow and text to Arrived. | 8 | 11 | 2023-11-29 | 2023-11-30 | High | Awais Subhani
When a Manifest has been created but not the receipt(s) generated, change the button color to white with green outline and text to Arrived to indicate partially complete. | 9 | 12 | 2023-12-01 | 2023-12-02 | High | Awais Subhani
Lot Transfer add cluster for available target locations lot transfer | 25 | 27 | 2023-12-10 | 2023-12-13 | High | Awais Subhani
Lot Transfer Cluster Edit populating pen and lot incorrectly | 20 | 18 | 2023-12-14 | 2023-12-17 | High | Awais Subhani
Lot Transfer default checkbox when location change not in cluster | 15 | 20 | 2023-12-18 | 2023-12-21 | High | Awais Subhani
Shipments from Schedule/Showlist - Headcount Default | 10 | 13 | 2023-01-14 | 2023-01-16 | High | Awais Subhani
Lot Ownership Assignment - Batch Assignment | 20 | 24 | 2023-01-17 | 2023-01-21 | High | Awais Subhani
Lot Expense validation check | 6 | 7 | 2023-01-23 | 2023-01-23 | High | Awais Subhani
Cattle Charges - Lot Expenses item dropdown not filtering for non-stock | 8 | 8 | 2023-01-24 | 2023-01-24 | High | Awais Subhani
Cattle Management - Delete Lot | 10 | 15 | 2023-01-27 | 2023-01-30 | High | Awais Subhani
Cattle Management - Lot - Add columns to Arrivals | 20 | 25 | 2023-02-02 | 2023-02-06 | High | Awais Subhani
Lot Expense - In Stock check not joining on LocationID | 20 | 18 | 2023-02-08 | 2023-02-11 | High | Awais Subhani
Catch Weights pen list showing 0 head pens for lot | 10 | 13 | 2023-02-18 | 2023-02-21 | High | Awais Subhani
Lot Transfer - Destination Restart lot ownership validation | 14 | 18 | 2023-02-24 | 2023-02-27 | High | Awais Subhani
Dynamic Closeout and Pensheet - Convert to use the Kendo Grid UI like controls | 25 | 35 | 2023-03-10 | 2023-03-14 | High | Awais Subhani
CV ¦ Nav database ¦ the Address,City issue | 10 | 18 | 2023-04-14 | 2023-04-17 | High | Awais Subhani
Lot Expense pen drop down after invoiced | 15 | 22 | 2023-04-28 | 2023-05-02 | High | Awais Subhani
Contact screen not in menu | 10 | 3 | 2023-05-07 | 2023-05-07 | High | Awais Subhani
Commodities - disable the In Stock at Location when it exists in active Ration | 20 | 30 | 2023-05-18 | 2023-05-23 | High | Awais Subhani
Ration Master - validate commodities In Stock status on save | 10 | 9 | 2023-05-24 | 2023-05-25 | High | Awais Subhani
Ration Master - edit Ingredients where commodity Is Stock = No | 13 | 15 | 2023-05-27 | 2023-05-29 | High | Awais Subhani